## Product Backlog
CAR RENTAL MANAGEMENT SYSTEM
PRODUCT BACKLOG
| TOTAL LOC |  | 1000 | Note: Total LOC should be >= 900 * Number of project members
Function Name | Feature | Complexity | LOC | Planned Code Iteration | Student No | In-charge Full Name | Actual Code Iteration | SRS Status | Design Status | Coding Status | Testing Status | % Completed | Completed in Iteration
View My Car | Manage Rental Car | Simple | 100 | Iteration 1 | HE150684 | Đỗ Đình Nam | Iteration 1 | Completed | Completed | Completed | Completed | 100 | Iteration 1
View Car Information | Manage Rental Car | Simple | 100 | Iteration 1 | HE150685 | Đỗ Đình Nam | Iteration 1 | Completed | Completed | Completed | Completed | 100 | Iteration 1
Add Basic Information | Manage Rental Car | Simple | 100 | Iteration 2 | HE150686 | Đỗ Đình Nam | Iteration 2 | Completed | Completed | Completed | Completed | 100 | Iteration 2
Add Advance Information | Manage Rental Car | Simple | 100 | Iteration 2 | HE150687 | Đỗ Đình Nam | Iteration 2 | Completed | Completed | Completed | Completed | 100 | Iteration 2
Set Rental Price | Manage Rental Car | Simple | 100 | Iteration 3 | HE150688 | Đỗ Đình Nam | Iteration 3 | Completed | Completed | Completed | Completed | 100 | Iteration 3
Upload Car Images | Manage Rental Car | Medium | 200 | Iteration 3 | HE150689 | Đỗ Đình Nam | Iteration 3 | Completed | Completed | Completed | Completed | 100 | Iteration 4
Upload Registration Certificate | Manage Rental Car | Complex | 300 | Iteration 4 | HE150690 | Đỗ Đình Nam | Iteration 3 | Completed | Completed | Completed | Completed | 100 | Iteration 4
-- | -- | Simple |  | Iteration 2 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 3 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 4 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 5 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 6 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 7 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 8 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 9 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 10 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 11 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 12 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 13 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 14 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 15 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 16 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 17 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 18 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 19 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 20 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 21 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 22 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 23 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 24 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 25 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 26 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 27 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 28 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 29 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 30 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 31 | -- | -- | Iteration 1 | [5 empty] | Iteration 1
-- | -- | Simple |  | Iteration 32 | -- | -- | Iteration 1 | [5 empty] | Iteration 1